Shape, rectangle

Description automatically generated

**Cancer Prevention at Your Fingertips, Empowering Veterans Through Mobile Application (CPMA)**

****IMPLEMENTATION GUIDE

**Table of Contents**

[Chapter 1: Welcome & Overview 3](#_Toc116303957)

[Acknowledgements 3](#_Toc116303958)

[Origin of Cancer Prevention at Your Fingertips, Empowering Veterans Through Mobile Application (CPMA) 4](#_Toc116303959)

[What is CPMA? 5](#_Toc116303960)

[How does this practice work? 5](#_Toc116303961)

[Chapter 2: Organizational Readiness 7](#_Toc116303962)

[Chapter 3: Implementation Roadmap 8](#_Toc116303963)

[Chapter 4: Implementation Phases 9](#_Toc116303964)

[Phase One: Design Phase 9](#_Toc116303965)

[Step One: Identify Practice Champion and Interdisciplinary Team 9](#_Toc116303966)

[Step Two: Set Project Scope and Charter 10](#_Toc116303967)

[Step Three: Engage all Relevant Stakeholders 11](#_Toc116303968)

[Phase Two: Planning Phase 13](#_Toc116303969)

[Step Four: Develop Protocol Template 13](#_Toc116303970)

[Step Five: Create Brochure and Marketing 14](#_Toc116303971)

[Step Six: CAC Order Modification 14](#_Toc116303972)

[Step Seven: Staff Training and Education 14](#_Toc116303973)

[Step Eight: Protocol Review and Resubmission (if required) 15](#_Toc116303974)

[Step Nine: Develop a Collection Plan for Monitoring Feedback Metrics 15](#_Toc116303975)

[Phase Three: Implementation Phase 16](#_Toc116303976)

[Step Ten: Pilot Testing 16](#_Toc116303977)

[Step Eleven: Lessons Learned, Final Review, and Resubmission (if required) 16](#_Toc116303978)

[Step Twelve: Live Launch 16](#_Toc116303979)

[Phase Four: Post-Implementation Phase 17](#_Toc116303980)

[Step Thirteen: Collect and Interpret Data 17](#_Toc116303981)

[Step Fourteen: Share Success with Stakeholders and Celebrate! 17](#_Toc116303982)

[Chapter 5: Resources 18](#_Toc116303983)

[Questions? 18](#_Toc116303984)

[Acronym Key 19](#_Toc116303985)

[Resource Links 19](#_Toc116303986)

[Other Helpful Links 20](#_Toc116303987)

[Attachments 20](#_Toc116303988)

**Chapter 1: Welcome & Overview**

**Welcome, and thank you for your participation implementing Cancer Prevention at Your Fingertips, Empowering Veterans Through Mobile Application (CPMA) at your facility.** This implementation guide is intended for interdisciplinary teams leading implementation at your facility.

****The goals of this implementation guide are to provide:

* Background Information on CPMA;
* Instructions for how to implement this practice at your facility;
* Access to marketing tools and staff education; and
* A roadmap for successful adoption and sustainability.

**Acknowledgements**

The following individuals were instrumental in developing and replicating CPMA:


* Tiniska (Jade) Brooks, Oncology Certified Nurse, [Tiniska.brooks@va.gov](mailto:Tiniska.brooks@va.gov)
* Samantha Hands, Clinical Nurse Leader/GI Department Champion, [Samanatha.hands@va.gov](mailto:Samanatha.hands@va.gov)
* Franklin Nduku, Magnet Director, [Franklin.nduku@va.gov](mailto:Franklin.nduku@va.gov)

**Origin of Cancer Prevention at Your Fingertips, Empowering Veterans Through Mobile Application (CPMA)**

A picture containing blue

Description automatically generatedIn the United States, Colorectal Cancer (CRC) is the third leading cause of cancer-related deaths in men and women and the second most common cause of cancer deaths of men and women combined. According to the American Cancer Society, CRC is expected to cause approximately 52,580 deaths in 2022.

CPMA was implemented in response to Michael E. DeBakey VA Medical Center in Houston, Texas (Houston VA) experiencing the highest volume of endoscopic procedures compared to other VA facilities in the U.S. In preliminary assessment, Houston VA found a high same-day cancellation rate of 20-30% per day. In lieu of these results, a process improvement emerged to minimize system-level delays and improve population-level survival outcomes through mobile integration, Annie Orion, in the ambulatory setting.

****

The Cancer Prevention at Your Fingertips, Empowering Veterans Through Mobile Applicationpractice is **1 of 10** Promising Practices to emerge from the seventh VHA Shark Tank Competition, selected from a **total of 323** practice submissions.

In 2021, the team at Houston VA applied to the seventh **Veterans Health Administration (VHA) Shark Tank Competition**, a Diffusion of Excellence initiative for sourcing clinical and operational Promising Practices that originate at VA facilities. After several rounds of rigorous evaluation from subject matter experts (SMEs) and program office representatives, the CPMA practice competed in VHA Shark Tank Competition and was designated as a Promising Practice and replicated at the Captain James A. Lovell Federal Health Care Center (VA Medical Center North Chicago).

**What is CPMA?**

CPMA is a colon preparation protocol developed by nursing staff in the Gastroenterology (GI) clinic in collaboration with an oncology nurse navigator. This practice empowers Veterans, active-duty service members, and their families through the utilization of a Short Message Service (SMS) text messaging service, Annie Orion.

CPMA works towards reducing same-day cancellations, increasing national awareness and adoption, encouraging innovation and system redesign, promoting innovation utilization in the ambulatory setting, and building relationships with national stakeholders.

**How does this practice work?**

Graphical user interface, application

Description automatically generatedCPMA utilizes, Annie Orion, a SMS text messaging capability that promotes self-care for Veterans, active-duty service members, and their families enrolled in the VA Health Care system by providing appointment reminders and preparation for their colonoscopies.

Annie Orion provides the ability to automatically send self-care reminders to patients and is designed to reinforce Veteran’s plan of care. It can be used with either a basic cell phone or smart phone and only for patients who agree to receive text message reminders from Annie Orion.

Driving VA’s strategic priorities as a High Reliability Organization (HRO), Annie Orion empowers, educates, and engages each patient from the convenience of their home. Developed by VHA, Annie Orion is intended to facilitate health behavior change among patients; and benefits patients by increasing independence and self-management skills.

To learn more about Annie Orion, please reference the *Annie Toolkit: Implementation Guide for Annie POCs and VA Staff to Increase Use of Annie in VA Clinics and Hospitals* attached in Table 4 in Chapter 5: Resources.

The process flow map in figure 1 below shows an example of how CPMA is implemented once an appointment is established by the medical support assistant (MSA).

Figure 1. Process Flow for CPMA Enrollment

**Diagram

Description automatically generated**

**Chapter 2: Organizational Readiness**

An Organizational Readiness Assessment can by employed to ensure maximum success in implementing CPMA. This assessment takes stock of your site’s existing processes, which is a key step in preparing for the assimilation of a new intervention into your facility’s culture and work systems. One way of approaching this is through the [Consolidated Framework for Implementation Research (CFIR)](https://cfirguide.org/), which is an implementation science model that offers several considerations to prepare your organization for a successful implementation. While any number of the CFIR considerations may be useful, we recommend focusing on evaluating your facility’s barriers and facilitators, and developing a plan to proceed by following these seven considerations:

1. Figure 2. Seven considerations when evaluating barriers and facilitators

A picture containing text

Description automatically generated

Refer to the [Attachments section in Table 4](#Attachments) for an embedded worksheet to assist your team in conducting this assessment. This exercise could shed valuable light on the existing work systems within your facility by identifying and planning for potential barriers, as well as understanding ways to leverage facilitators. Each consideration will allow you and your team to increase the likelihood of a successful implementation!

**Chapter 3: Implementation Roadmap**

Implementation of CPMA is estimated to take 1-6 months, however this can vary based on buy-in, stakeholder engagement, and protected time. Implementation can move quickly if your project facilitator/GI Nurse is provided with protected time, approximately 2-5 hours per week, or as determined by your implementation team.

Figure 3 provides a high-level roadmap for implementation.

1. Figure 3. Implementation Roadmap Overview for CPMA

|  |  |
| --- | --- |
| **­ Phase One: Design Phase**  (Months 0-1) | Step 1: Identify Practice Champion and Interdisciplinary Team |
| Step 2:Set Project Scope and Charter (Optional) |
| Step 3: Engage all Relevant Stakeholders |
| **Phase Two: Planning Phase**  (Months 1-3) | Step 4: Develop Protocol Template |
| Step 5: Create Brochure and Marketing |
| Step Six: CAC Order Modification |
| Step 7: Staff Training and Education |
| Step 8: Protocol Review and Resubmission (if required) |
|  | Step 9: Develop a Collection Plan for Monitoring Feedback Metrics |
| **Phase Three: Implementation Phase**  (Months 3-5) | Step 10: Practice Go-Live |
| Step 11: Lessons Learned, Final Review, and Resubmission (if required) |
|  | Step 12: Live Launch |
| **Phase Four: Post-Implementation Phase**  (Months 5-6) | Step 13: Collect and Interpret Data |
| Step 14: Share Success and Celebrate! |

**Chapter 4: Implementation Phases**


**Phase One: Design Phase**

**Step One: Identify Practice Champion and Interdisciplinary Team**

Implementation of this practice requires action from your facility’s GI Department and Annie Orion. We highly recommend determining a Champion within your GI Department who will acts as the Physician Champion to engage with patients. It is recommended to determine the GI Champion prior to implementation or within the first two weeks of implementation.

**My HealtheVet**

Establish a point of contact with your local My HealtheVet Coordinator to ensure a connection to care and a connection to the Annie Orion application. It is recommended to establish this relationship within the first two weeks of implementation.



Next, identify the My HealtheVet Coordinator at your facility and provide an introduction of the CPMA practice and your team to seek approval to launch this practice.

My HealtheVet is VA’s online Personal Health Record system for Veterans, active-duty service members, their dependents, and caregivers. The My HealtheVet Coordinator will act as a key stakeholder for facilitating your team’s relationship with the Office of Connected Care and promoting the utilization of the Annie Orion application.

Contact Annie Orion to request a point of contact for your partnership and to be assigned a program editor.

**Step Two: Set Project Scope and Charter**

While establishing scope and creating a charter is not required, many facilities have found a project charter helps guide the implementation of the practice. This step is especially helpful if you are experiencing any barriers or pushback from leadership or other important stakeholders.

As with many Promising Practices identified through Diffusion of Excellence, CPMA can be modified to fit the needs of your medical center. Certain aspects of the practice are flexible and should be discussed with the Interdisciplinary Team and then documented in the Project Charter (*template options* [*attached in Table 4*](#Attachments)). For example, the following bullets highlight some of the flexible components of the practice:

* If your facility experiences cultural resistance to change with implementing a new process or does not have department buy-in, then promote it as process development and provide additional training and education.
* If Veterans are struggling with accessibility (texting rates, device plan, usability, device services, etc.), then provide information related to Wi-Fi mitigation for costs, financial protocol, and additional promotion and awareness.
* If your proposed protocol requires revisions as determined by Annie Orion, then revise and resubmit.

The **Project Charter** serves as a guide for implementing this practice and includes:

* General project description
* Scope of implementing this practice (e.g., which units to involve)
* Problem/opportunity statement to be addressed by implementing the practice
* Facility goals for implementation
* Facility timeline for implementation
* Resources your facility will need to obtain
* Team members and leadership who will support implementation (see **Step 1**), and their respective time commitments

**Step Three: Engage all Relevant Stakeholders**

You will want to identify all stakeholders needed to successfully implement this practice, determine department buy-in, and establish roles and responsibilities.

Refer to Table 1 below for a list of the commonly involved stakeholder groups. When you initially engage these groups for implementation at your site, consider how you can best communicate with them to get the response you need.

Table 1. Implementation Overview for CPMA

|  |  |
| --- | --- |
| Stakeholder Group  (From whom do I need help?) | Dependencies  (What do I need from them?) |
| GI Department Champion/Nurse Manager | Program Support, Process Owner, and Content Development |
| My HealtheVet Coordinator | Program Buy-in and Program Support |
| Annie Orion Point of Contact | SMS Template Creation and Troubleshooting |
| CAC | Program Support and Template Development |
| High Reliability Organization (HRO) | Program Buy-in and Support |
| Primary Care Office | Patient Engagement |
| Whole Health | Patient Engagement |
| Members of Quality/Medical Support Assistant Group Practice Manager | Data Collection, Patient Enrollment, Mailout Distribution, Care Coordination, and Standardization. |

**Remember:** Your facility might have additional stakeholders that you need to engage, so be sure to tailor this list to fit your facility needs!

Once you have determined the stakeholder groups and individuals to engage, you may want to host a meeting with your team members to present the project charter and provide background on the Practice and the implementation process. We have provided resource materials to assist you with engaging stakeholders in Chapter 5. Feel free to tailor the materials to be specific to your facility.



After meeting with team members and working with them to refine the project charter, meet with your facility’s leadership and present the final project charter to obtain their buy-in and approval. Leadership may also be able to provide information and support around addressing potential challenges and obtaining resources.

**Remember:** It is important to maintain regular stakeholder engagement during this phase, so we recommend monthly updates to less-involved stakeholders. During your first meeting with them, ask them how they would like to stay engaged in this process (email, in-person, etc.).

**HIGHLY RECOMMENDED!**

**HRO Buy-in:** Secure HRO institutional buy-in for your practice. This may require scheduling meetings to provide an overview of CPMA. It is recommended to secure buy-in within the first three months of implementation.

**Primary Care/Whole Health:** Engage with Primary Care Physicians and your facility’s Whole Health Team to engage with patients and refer to CPMA practice. It is recommended to build these relationships within the first month of implementation.



**Phase Two: Planning Phase**

**Step Four: Develop Protocol Template**

To successfully implement this practice, your team will need to develop a protocol template. Your team along with your Annie Orion Contact will determine an appropriate template to be used for patients being referred.

It is important to incorporate a protocol review by the Annie Orion Application Team into your timeline, as you maybe need to resubmit your proposed protocol.

Refer to the example protocol template in Figure 3 below:

1. Figure 3: Example Protocol Template

**A picture containing timeline

Description automatically generated**

**Step Five: Create Brochure and Marketing**

You need to create a Brochure to promote and explain the CPMA practice to clinical staff and patients.

1. Timeline

   Description automatically generatedGraphical user interface

   Description automatically generatedExample of Brochure Front and Back

**Step Six: CAC Order Modification**

Request a Clinical Application Coordinator (CAC) order modification.

CPRS corresponding note title must undergo a facility review per institutional policy. Item is used to confirm veteran consent of Annie and financial expenses incurred with SMS usage.

**Step Seven: Staff Training and Education**

Begin to conduct staff training and education. It is recommended to market the kick-off of your CPMA practice with a minimum of two weeks of promotion prior to the live launch.

The GI Clinical Champion will conduct training ([refer to *Annie Orion 4.2 Clinician (End User) Training* in Table 4](#Attachments)) with the assigned GI Clinical staff to provide education on the CPMA practice and the utilization of Annie Orion application. Additionally, practice staff can refer to the *Annie Toolkit: Implementation Guide for Annie Orion POCs and VA Staff to Increase Use of Annie in VA Clinics and Hospitals* embedded in Table 4.

**Step Eight: Protocol Review and Resubmission (if required)**

Review the protocol and resubmit to your Annie Orion Contact if necessary.

**Step Nine: Develop a Collection Plan for Monitoring Feedback Metrics**

To monitor feedback metrics, it is recommended to determine an appropriate platform for survey development. It is suggested to create a survey six weeks prior to launching the practice to assess staff and patient experience.

**Potential Monitoring and Feedback Metrics**

Implementation can be assessed through both **process measures** and **outcome measures**. We recommend using process measures to assess how the implementation is going for your team. We also recommend the use of outcome measures to assess the success of the program from the Veteran perspective.

Ideas for **process measures:**

* Cancellation Rates Annie Orion Users v. Non-Users
* Enrollment Rate
* Internal Brochure Distribution

Ideas for **outcome measures:**

* Boston Bowel Prep Scores
* Patient Satisfaction
* Cost Analysis

**Phase Three: Implementation Phase**

**Step Ten: Pilot Testing**

At this point, your team can begin pilot testing and conduct a final review of the protocol.

During the pilot test, key stakeholders need to be engaged to implement the following:

* **Patient Education:** Conduct patient education in collaboration with the identified GI Clinical Champion. The goal of patient education is to teach patients about the program and provide program awareness.
* **Patient Enrollment:** Conduct patient enrollment with the assistance of the assigned Medical Support Assistance Group Practice Manager. Patient enrollment will be obtained through care coordination and mailout distribution.

**Step Eleven: Lessons Learned, Final Review, and Resubmission (if required)**

Assess to understand the challenges during pilot testing. Make adjustments where necessary for smoother implementation. For example, one lesson learned from Michael E. DeBakey VA Medical Center was to educate the care team early and often.

Make a final review of the protocol and resubmit to your Annie Orion Contact, if necessary.

**Step Twelve: Live Launch**

Set a go-live date and coordinate a two-week promotion leading up to the kick-off.

Go live and continue to educate staff and patients!

**Phase Four: Post-Implementation Phase**

**Step Thirteen: Collect and Interpret Data**

To monitor the goal of reducing same-day cancellations for outpatients, focus on collecting same-day cancellation rates for endoscopic procedures. This will be done through your local Members of Quality/Medical Support Assistance Group Practice Manager.

**Step Fourteen: Share Success with Stakeholders and Celebrate!**

Be sure to share your success with leadership and other stakeholders to gain their continued support.

Celebrating reaching 1000th Veteran with CPMA in Houston.

Celebration is of course an optional step, but after successfully implementing CPMA at your facility, you and your team deserve recognition and celebration! Regardless of the format you choose, it is important to celebrate the hard work put forth and the outcomes accomplished, because this practice directly enhances the experience of the Veterans that visit your facility.

**Chapter 5: Resources**

**Questions?**

Do you have questions or need advice about implementing CPMA at your facility?

Check out the CPMA Diffusion Marketplace page and our SharePoint site!

* Marketplace: [Diffusion Marketplace (va.gov)](https://marketplace.va.gov/innovations/cancer-prevention-at-your-fingertips-empowering-veterans-through-mobile-application)
* [SharePoint Link](https://teams.microsoft.com/_#/files/Cancer%20Prevention%20at%20Your%20Fingertips?threadId=19%3A3644177e6962438d85f9c2b82b66844b%40thread.tacv2&ctx=channel&context=Cancer%2520Prevention%2520at%2520Your%2520Fingertips&rootfolder=%252Fsites%252FDiffusionofExcellenceCohort7-CancerPreventionatYourFingertips%252FShared%2520Documents%252FCancer%2520Prevention%2520at%2520Your%2520Fingertips)

Or contact:

* Tiniska (Jade) Brooks, Oncology Certified Nurse, [Tiniska.brooks@va.gov](mailto:Tiniska.brooks@va.gov)
* Samantha Hands, Clinical Nurse Leader/GI Department Champion, [Samanatha.hands@va.gov](mailto:Samanatha.hands@va.gov)
* Franklin Nduku, Magnet Director, [Franklin.nduku@va.gov](mailto:Franklin.nduku@va.gov)

**Acronym Key**

Table 2. Acronym Key

|  |  |  |
| --- | --- | --- |
| Acronym | Definition | |
| CPMA | Cancer Prevention at Your Fingertips, Empowering Veterans Through Mobile Application |
| VHA | Veterans Health Administration |
| MSA | Medical Support Assistant |
| SME | Subject Matter Expert |
| CRC | Colorectal Cancer |
| SMS | Short Message Service |
| HRO | High Reliability Organization |
| GI | Gastroenterology |
| CAC | Clinical Application Coordinator |
| HRO | High Reliability Organization |

**Resource Links**

Table 3. Resources for CPMA

|  |  |
| --- | --- |
| Resource | Link |
| Annie Roles Checklist | [Annie\_Roles\_Checklist.pdf (amazonaws.com)](https://prod-dm.s3.us-gov-west-1.amazonaws.com/practice_resources/attachments/000/000/871/original/Annie_Roles_Checklist.pdf?X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Credential=ASIAR2ERFC2NEFZCNIW2%2F20220816%2Fus-gov-west-1%2Fs3%2Faws4_request&X-Amz-Date=20220816T120959Z&X-Amz-Expires=2700&X-Amz-Security-Token=FwoDYXdzENH%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaDKxh0voTr9mX1nFRTCKDBLAP9GezO%2FdFnudOSDnkeMCYJqGNYanHUe8dYbvEbviyI6ngTCAxrXlNe14blhAg0A9jb%2Bg3vj5Hh3aoe4TGtdnHHkESLMiZzNo7eNAhLK4C7XR9ngCaHLJzsnr31eUlOcZgpoVJ1uXb4EGjVom7Ju9UL1PEwms6W%2BeNX6D6ISUQSzUjzy0DHA5nv1ESNsusRgwuvGpzjTJCjTnQJSur4kPJPBHyOt54bGAG5cXxyt3YRIrthfOn6nWbJ%2F0nAdF%2FcPNLQlyKBx0ZY3E6KEBxqTBKjKfXPnZ3AmhDXlouw2%2BmU4MEUg8lnEtyd3AplqeIrbUeKsdg5J1stM28g4r3cpypCYuniwIQ2z4XY%2F4%2BPLrp%2F5rfn0kcBvRgIUSOuEZYwksewHU8NeaUJeLbuEny%2B8wa3bq2gPIkfT8IR12e4dUPKYFyx9e25OX8XFmOUs6KBCaEXAq3XgVO9brSTwgzpQHTGUkH9YItnuHJZYvXMuvbNnK8CuAMnWkyRTX4%2BYvV89fFRyftgJa3WhupKJylTzEeGExI9kVCNmZMSZAFU0oksUwGsQPszO6O%2BewiQqIPJFnJxZHOl%2Fh8FFUslsag9CvZ%2Bo1fOJO4CQD1FoBrmeyfEzBcxkkLgqs50s21Y5ksYGh%2BT%2FnykXXstnanOqmom9hMDLQRosML6ETb%2B6BhHs8AavztKLvj7ZcGMjmvVrSEiL1y%2FM6rmKo6RseNXYI2Y%2F%2F68jZ4FiDK%2F2LqpILTH2PUdOwsGm2QWOnc%2BhV7HVFQ%2FdIuwLc%3D&X-Amz-SignedHeaders=host&X-Amz-Signature=138a8f52e4cf929280e42b65db34da689b76f19af5015ace63479c960ef3f4a0) |
| Annie 14 Day Protocol | [Microsoft Word - Day 15\_Annie Template Day Zero\_PDSA 2 (amazonaws.com)](https://prod-dm.s3.us-gov-west-1.amazonaws.com/practice_solution_resources/attachments/000/000/074/original/Day14_Annie_Protocol-HOU-LT2314779.pdf?X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Credential=ASIAR2ERFC2NEFZCNIW2%2F20220816%2Fus-gov-west-1%2Fs3%2Faws4_request&X-Amz-Date=20220816T120959Z&X-Amz-Expires=2700&X-Amz-Security-Token=FwoDYXdzENH%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaDKxh0voTr9mX1nFRTCKDBLAP9GezO%2FdFnudOSDnkeMCYJqGNYanHUe8dYbvEbviyI6ngTCAxrXlNe14blhAg0A9jb%2Bg3vj5Hh3aoe4TGtdnHHkESLMiZzNo7eNAhLK4C7XR9ngCaHLJzsnr31eUlOcZgpoVJ1uXb4EGjVom7Ju9UL1PEwms6W%2BeNX6D6ISUQSzUjzy0DHA5nv1ESNsusRgwuvGpzjTJCjTnQJSur4kPJPBHyOt54bGAG5cXxyt3YRIrthfOn6nWbJ%2F0nAdF%2FcPNLQlyKBx0ZY3E6KEBxqTBKjKfXPnZ3AmhDXlouw2%2BmU4MEUg8lnEtyd3AplqeIrbUeKsdg5J1stM28g4r3cpypCYuniwIQ2z4XY%2F4%2BPLrp%2F5rfn0kcBvRgIUSOuEZYwksewHU8NeaUJeLbuEny%2B8wa3bq2gPIkfT8IR12e4dUPKYFyx9e25OX8XFmOUs6KBCaEXAq3XgVO9brSTwgzpQHTGUkH9YItnuHJZYvXMuvbNnK8CuAMnWkyRTX4%2BYvV89fFRyftgJa3WhupKJylTzEeGExI9kVCNmZMSZAFU0oksUwGsQPszO6O%2BewiQqIPJFnJxZHOl%2Fh8FFUslsag9CvZ%2Bo1fOJO4CQD1FoBrmeyfEzBcxkkLgqs50s21Y5ksYGh%2BT%2FnykXXstnanOqmom9hMDLQRosML6ETb%2B6BhHs8AavztKLvj7ZcGMjmvVrSEiL1y%2FM6rmKo6RseNXYI2Y%2F%2F68jZ4FiDK%2F2LqpILTH2PUdOwsGm2QWOnc%2BhV7HVFQ%2FdIuwLc%3D&X-Amz-SignedHeaders=host&X-Amz-Signature=11ce262e4dd021cc9779daf90c285dfc3374a05ac11b87f7d995429cb120427a) |
| Annie Program Outcome Data Graphics | [Data\_Charts\_Annie\_.pdf (amazonaws.com)](https://prod-dm.s3.us-gov-west-1.amazonaws.com/practice_results_resources/attachments/000/000/073/original/Data_Charts_Annie_.pdf?X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Credential=ASIAR2ERFC2NEFZCNIW2%2F20220816%2Fus-gov-west-1%2Fs3%2Faws4_request&X-Amz-Date=20220816T120959Z&X-Amz-Expires=2700&X-Amz-Security-Token=FwoDYXdzENH%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaDKxh0voTr9mX1nFRTCKDBLAP9GezO%2FdFnudOSDnkeMCYJqGNYanHUe8dYbvEbviyI6ngTCAxrXlNe14blhAg0A9jb%2Bg3vj5Hh3aoe4TGtdnHHkESLMiZzNo7eNAhLK4C7XR9ngCaHLJzsnr31eUlOcZgpoVJ1uXb4EGjVom7Ju9UL1PEwms6W%2BeNX6D6ISUQSzUjzy0DHA5nv1ESNsusRgwuvGpzjTJCjTnQJSur4kPJPBHyOt54bGAG5cXxyt3YRIrthfOn6nWbJ%2F0nAdF%2FcPNLQlyKBx0ZY3E6KEBxqTBKjKfXPnZ3AmhDXlouw2%2BmU4MEUg8lnEtyd3AplqeIrbUeKsdg5J1stM28g4r3cpypCYuniwIQ2z4XY%2F4%2BPLrp%2F5rfn0kcBvRgIUSOuEZYwksewHU8NeaUJeLbuEny%2B8wa3bq2gPIkfT8IR12e4dUPKYFyx9e25OX8XFmOUs6KBCaEXAq3XgVO9brSTwgzpQHTGUkH9YItnuHJZYvXMuvbNnK8CuAMnWkyRTX4%2BYvV89fFRyftgJa3WhupKJylTzEeGExI9kVCNmZMSZAFU0oksUwGsQPszO6O%2BewiQqIPJFnJxZHOl%2Fh8FFUslsag9CvZ%2Bo1fOJO4CQD1FoBrmeyfEzBcxkkLgqs50s21Y5ksYGh%2BT%2FnykXXstnanOqmom9hMDLQRosML6ETb%2B6BhHs8AavztKLvj7ZcGMjmvVrSEiL1y%2FM6rmKo6RseNXYI2Y%2F%2F68jZ4FiDK%2F2LqpILTH2PUdOwsGm2QWOnc%2BhV7HVFQ%2FdIuwLc%3D&X-Amz-SignedHeaders=host&X-Amz-Signature=bf447af7ab37cd46465cc61bc709460e421616a74a8881b98c8e4cb3c95e0a1a) |
| Annie App for Veterans Video | <https://youtu.be/U4Ot6EDhFrA> |
| Colon Cancer a Silent Killer | <https://youtu.be/DRVZKTISsGg> |
| Annie Implementation Checklist | [Annie\_Implementation\_Facility\_Checklist.pdf (amazonaws.com)](https://prod-dm.s3.us-gov-west-1.amazonaws.com/practice_resources/attachments/000/000/870/original/Annie_Implementation_Facility_Checklist.pdf?X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Credential=ASIAR2ERFC2NEFZCNIW2%2F20220816%2Fus-gov-west-1%2Fs3%2Faws4_request&X-Amz-Date=20220816T120959Z&X-Amz-Expires=2700&X-Amz-Security-Token=FwoDYXdzENH%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaDKxh0voTr9mX1nFRTCKDBLAP9GezO%2FdFnudOSDnkeMCYJqGNYanHUe8dYbvEbviyI6ngTCAxrXlNe14blhAg0A9jb%2Bg3vj5Hh3aoe4TGtdnHHkESLMiZzNo7eNAhLK4C7XR9ngCaHLJzsnr31eUlOcZgpoVJ1uXb4EGjVom7Ju9UL1PEwms6W%2BeNX6D6ISUQSzUjzy0DHA5nv1ESNsusRgwuvGpzjTJCjTnQJSur4kPJPBHyOt54bGAG5cXxyt3YRIrthfOn6nWbJ%2F0nAdF%2FcPNLQlyKBx0ZY3E6KEBxqTBKjKfXPnZ3AmhDXlouw2%2BmU4MEUg8lnEtyd3AplqeIrbUeKsdg5J1stM28g4r3cpypCYuniwIQ2z4XY%2F4%2BPLrp%2F5rfn0kcBvRgIUSOuEZYwksewHU8NeaUJeLbuEny%2B8wa3bq2gPIkfT8IR12e4dUPKYFyx9e25OX8XFmOUs6KBCaEXAq3XgVO9brSTwgzpQHTGUkH9YItnuHJZYvXMuvbNnK8CuAMnWkyRTX4%2BYvV89fFRyftgJa3WhupKJylTzEeGExI9kVCNmZMSZAFU0oksUwGsQPszO6O%2BewiQqIPJFnJxZHOl%2Fh8FFUslsag9CvZ%2Bo1fOJO4CQD1FoBrmeyfEzBcxkkLgqs50s21Y5ksYGh%2BT%2FnykXXstnanOqmom9hMDLQRosML6ETb%2B6BhHs8AavztKLvj7ZcGMjmvVrSEiL1y%2FM6rmKo6RseNXYI2Y%2F%2F68jZ4FiDK%2F2LqpILTH2PUdOwsGm2QWOnc%2BhV7HVFQ%2FdIuwLc%3D&X-Amz-SignedHeaders=host&X-Amz-Signature=749ae9b4cac2f396653127d334057a468a5d37e4373b522bd334aaeefd7a926c) |
| Annie App for Clinicians | [Annie App for Clinicians | VA Mobile](https://mobile.va.gov/app/annie-app-clinicians) |
| Annie User Manual | [Annie App for Veterans – User Manual (va.gov)](https://mobile.va.gov/sites/default/files/user-manual-annie-app-veterans.pdf) |

**Other Helpful Links**

* [Colorectal Cancer Statistics | How Common Is Colorectal Cancer?](https://www.cancer.org/cancer/colon-rectal-cancer/about/key-statistics.html)

**Attachments**

Table 4. Attachments for CPMA

| Document | File |
| --- | --- |
| Organizational Readiness Assessment |  |
| Project Charter Template 1 |  |
| Project Charter Template 2 |  |
| Annie 4.2 Clinician (End User) Training |  |
| Annie Toolkit: Implementation Guide for Annie POCs and VA Staff to Increase Use of Annie in VA Clinics and Hospitals |  |
| Annie Information Disclosure Factsheet |  |
| Annie Sample Note |  |
| Annie Colonoscopy Prep Instructions Template |  |
| Houston MEDVA Annie Protocol |  |
| Mini-Z Tool |  |
| Put Annie on the CPRS Tools Menu |  |